| 19TH NOVEMBER 2025: Task Force Experts Sub- Teams travel to Pemba. |  |  |
| --- | --- | --- |
| 20TH NOVEMBER 2025: Day One Field Work on Wider Stakeholder Groups Consultations at Micheweni and Wete Districts. |  |  |
| 8AM – 10AM | Courtesy call at District level (DC and DED): A brief on 3 main presentations. | Task Force Experts Sub- Team |
| 10AM – 3PM | Consultative Meeting with the District’s Technical Experts, District Peace and Security Committee: Detailed discussion on the 3 main presentations. | Task Force Experts Sub- Team |
| 21st NOVEMBER 2025: Day Two Field Work on Wider Stakeholder Groups Consultations at Micheweni and Wete. |  |  |
| 9AM – 3PM | - Consultations with the Local Community Representatives: Detailed discussion on the 3 main presentations. - Draft presentation for consultation process feedback sharing. | Task Force Experts Sub- Team |
| 22nd NOVEMBER 2025: Day One Field Work on Wider Stakeholder Groups Consultations at Chakechake District |  |  |
| 8AM – 10AM | Courtesy call at District level (DC and DED): A brief on 3 main presentations. | Task Force Experts Sub- Team |
| 10AM – 3PM | Consultative Meeting with the District’s Technical Experts, District Peace and Security Committee: Detailed discussion on the 3 main presentations. | Task Force Experts Sub- Team |
| 24TH NOVEMBER 2025: Day Two Field Work on Wider Stakeholder Groups Consultations at Chakechake District. |  |  |
| 9AM – 3PM | - Consultations with the Local Community Representatives: Detailed discussion on the 3 main presentations. - Draft presentation for consultation process feedback sharing. | Task Force Experts Sub- Team |
| 25TH NOVEMBER 2025: Day One Field Work on Wider Stakeholder Groups Consultations at Mkoani District Council |  |  |
| 8AM – 10AM | Courtesy call at District level (DC and DED): A brief on 3 main presentations. | Task Force Experts Sub- Team |
| 10AM – 3PM | Consultative Meeting with the District’s Technical Experts, District Peace and Security Committee: Detailed discussion on the 3 main presentations. | Task Force Experts Sub- Team |
| 26TH NOVEMBER 2025: Day Two Field Work on Wider Stakeholder Groups Consultations at Mkoani District . |  |  |
| 9AM – 3PM | - Consultations with the Local Community Representatives: Detailed discussion on the 3 main presentations. - Draft presentation for consultation process feedback sharing. | Task Force Experts Sub- Team |