FIRST MEETING AND WIDER STAKEHOLDER GROUPS CONSULTATION FOR THE TASK FORCE TEAM OF EXPERTS ON NOMINATION PROCES OF THE PROPOSED TANGA – PEMBA SEASCAPE (TAPE-SEA) BIOSPHERE RESERVE

16th - 27TH NOVEMBER 2025

TENTATIVE AGENDA PROGRAMME

| TIME | EVENT | RENSPONSIBLE |
| --- | --- | --- |
| 16th NOVEMBER 2025: Participants travel from their respective working station to Bagamoyo. |  |  |
| 17th NOVEMBER 2025: Day One Meeting at Bagamoyo (Millennium Sea Breeze Resort) |  |  |
| 8:30- 8:40 | Arrival at meeting venue | All participants |
| 8:40- 9:00 | Registration | Secretariat - NATCOM |
| 9:00- 9:05 | Welcoming note and meeting objectives | NATCOM Official |
| 9:05- 9:20 | Round Table Introduction | All participants |
| 9:20 -9:25 | Brief overview of the process for the nomination of Task Force Team of Experts. | NATCOM Official |
| 9:25 – 9: 40 | Opening Remarks and Official launching of the Task Force | Executive Secretary - NATCOM |
| 9:40-10:40 | TEA BREAK (Including Group Photo) | ALL |
| 10:40- 11:00 | UNESCO NATCOM Mandates and Roles in brief | Dr. Joel Samuel |
| 11:00 – 11:30 | Proposal for nomination of the proposed Tanga – Pemba Seascape (T-P SEA) Biosphere Reserve | IUCN (Coordinator) |
| 11:30 - 12:00 | Review of draft zonation maps for the proposed Tanga – Pemba Seascape (T-P SEA) Biosphere Reserve | IUCN - GIS Expert |
| 12:00- 13:00 | General Guided Discussion (Including Questions and Answers) | Chairperson |
| 12:00 – 12: 20 |  |  |
| 12:20 – 13:00 |  |  |
| 13:00 -14:00 | LUNCH BREAK | ALL |
| 14.00 – 17: 20 | Going through BR Nomination Form | Dr. Henry Ndangalasi |
|  | Presentation of checklist and Annexes for BR Nomination Form | Mr. Jairos Mahenge |
|  | Discussions with respect to (T-P SEA) | Chairperson |
| 18th NOVEMBER 2025: Day Two Meeting at Bagamoyo (Conference TDB) |  |  |
| Morning session | Modality for wider stakeholder groups consultations: - Strategic formulation of two Special Task Force Experts Sub- Teams for Pemba and Tanga (Including Electing Leaders) - Review proposed identified stakeholder groups - Identify key issues and areas for concentration and follow-up in the field (i.e., community activities, land use conflicts, community resources use, iconic features). | Task Force Experts |
| Afternoon session | Modality for wider stakeholder groups consultations: - Prepare talking points for 3 main presentations: - Concept of Man and Biosphere – MAB - Brief progress on Biosphere Reserves in Tanzania - The proposed TAPE-SEA Biosphere Proposal. - Preparation of awareness materials. - Agree and prepare format for sharing feedback from field consultation process. - Develop action plan and provisional programme for the consultation process in Tanga and Pember (Including getting relevant Authorities for signatures) | Task Force Experts |
| 19th NOVEMBER 2025: Task Force Experts Sub- Teams travel to Pemba and Tanga respectively |  |  |
| 20th NOVEMBER 2025: Day One Field Work on Wider Stakeholder Groups Consultations at District Number One. |  |  |
| 8AM – 10AM | Courtesy call at District level (DC and DED): A brief on 3 main presentations. | Task Force Experts Sub- Team |
| 10AM – 3PM | Consultative Meeting with the District’s Technical Experts, District Peace and Security Committee: Detailed discussion on the 3 main presentations. | Task Force Experts Sub- Team |
| 21st NOVEMBER 2025: Day Two Field Work on Wider Stakeholder Groups Consultations at District Number One. |  |  |
| 9AM – 3PM | - Consultations with the Local Community Representatives: Detailed discussion on the 3 main presentations. - Draft presentation for consultation process feedback sharing. | Task Force Experts Sub- Team |
| 22th NOVEMBER 2025: Day One Field Work on Wider Stakeholder Groups Consultations at District Number Two |  |  |
| 8AM – 10AM | Courtesy call at District level (DC and DED): A brief on 3 main presentations. | Task Force Experts Sub- Team |
| 10AM – 3PM | Consultative Meeting with the District’s Technical Experts, District Peace and Security Committee: Detailed discussion on the 3 main presentations. | Task Force Experts Sub- Team |
| 24th NOVEMBER 2025: Day Two Field Work on Wider Stakeholder Groups Consultations at District Number Two. |  |  |
| 9AM – 3PM | - Consultations with the Local Community Representatives: Detailed discussion on the 3 main presentations. - Draft presentation for consultation process feedback sharing. | Task Force Experts Sub- Team |
| 25th NOVEMBER 2025: Day One Field Work on Wider Stakeholder Groups Consultations at District Number Three |  |  |
| 8AM – 10AM | Courtesy call at District level (DC and DED): A brief on 3 main presentations. | Task Force Experts Sub- Team |
| 10AM – 3PM | Consultative Meeting with the District’s Technical Experts, District Peace and Security Committee: Detailed discussion on the 3 main presentations. | Task Force Experts Sub- Team |
| 26th NOVEMBER 2025: Day Two Field Work on Wider Stakeholder Groups Consultations at District Number Three. |  |  |
| 9AM – 3PM | - Consultations with the Local Community Representatives: Detailed discussion on the 3 main presentations. - Draft presentation for consultation process feedback sharing. | Task Force Experts Sub- Team |
| 27th NOVEMBER 2025: Task Force Experts Sub- Teams from Pemba and Tanga travel back to Bagamoyo. |  |  |